## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 5 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS | (1 period is a week of work starting) (1 period is 18.9 - 24.9)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
[6 empty] | 18.9-24.9 | 25.9-1.10 | 2.10-8.10 | 9.10-15.10 | 16.10-22.10 | 23.10-29.10 | 30.10-5.11 | 6.11-12.11 | 13.11-19.11 | 20.11-26.11 | 27.11-3.12 | 4.12-10.12 | 11.12-17.12 | 18.12-24.12 | 25.12-31.12 | 1.1-7.1 | 8.1-14.1 | 15.1-21.1 | 22.1-28.1 | 29.1-4.2 | 5.2-11.2 | 12.2-18.2 | 19.2-25.2 | 26.2-3.3 | 4.3-10.3 | 11.3-17.3
[6 empty] | Září |  | Říjen |  |  |  | Listopad |  |  |  | Prosinec |  |  |  |  | Leden |  |  |  | Únor |  |  |  |  | Březen
Počáteční průzkum tématu | 1 | 6 | 1 | 9 | 60%
Výběr a objednání kamery | 2 | 2 | 1 | 8 | 100%
Zkouška jak moc data můžu upravovat | 4 | 3 | 8 | 3 | 20%
Realizace HW | 4 | 4 | 0 | 0 | 0%
HW - Poloha kamery | 4 | 1 | 0 | 0 | 0%
HW - Přenos Dat | 5 | 2 | 0 | 0 | 0%
HW - Ukládání dat | 7 | 1 | 0 | 0 | 0%
Sbírání dat | 8 | 2 | 0 | 0 | 0%
Uprava dat pro učení (Značkování) | 10 | 3 | 0 | 0 | 0%
Trénování modelu | 12 | 3 | 0 | 0 | 0%
Nasazení systému | 15 | 2 | 0 | 0 | 0%
Odladění systému | 17 | 4 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0 | 0%